## PMR (JULY-DECEMBER 2025)
DEPARTMENT OF EDUCATION
Region I
Schools Division Office
San Carlos City (Pangasinan)
PROCUREMENT MONITORING REPORT FOR SECOND SEMESTER OF FY 2025 (JULY-DECEMBER 2025)
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
310300100003000 | PROCUREMENT OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN, VENUE AND ACCOMMODATION (LIVE-IN) FOR THE CONDUCT OF CLUSTER ADM CONVERGENCE AMONG SOUTHWESTERN SDO OF REGION I (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 07/16/25 | NA | 07/21/25 | 07/21/25 | 07/21/25 | NA | 07/21/25 | 07/30/25 | 2025-08-10 | 2025-08-10 | 08/10/25 | 08/10/25 | ROI-25-0051 | 390000 | 390000 |  | 388050 | 388050 |  | NA | NA | NA | NA | NA | NA | IAR # 20250810-001 | Completed
310300100003000 | PROCUREMENT OF MEALS AND SNACKS FOR THE LEARNERS AND TEACHERS INVOLVED ON BENCHMARKING | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-03 | NA | 2025-07-10 | 2025-07-10 | 2025-07-10 | NA | 2025-07-10 | 07/14/25 | 07/16/25 | 07/16/25 | 08/13/25 | 08/13/25 | ROI-25-0051 | 50000 | 50000 |  | 48300 | 48300 |  | NA | NA | NA | NA | NA | NA | IAR # 20250813-001A | Completed
310300100003000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF CLUSTER ADM CONVERGENCE AMONG SOUTHWESTERN SDO OF REGION I (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 07/16/25 | NA | 07/21/25 | 07/21/25 | 07/21/25 | NA | 07/21/25 | 22/07/25 | 2025-07-31 | 07/31/25 | 2025-08-04 | 2025-08-04 | ROI-25-0051 | 97495 | 97495 |  | 93945 | 93945 |  | NA | NA | NA | NA | NA | NA | IAR # 20250804-002 | Completed
310200100005000 | PROCUREMENT AND DEPLOYMENT OF ADDITIONAL COMPUTER COMPONENTS AND NETWORK DEVICES FOR THE REPLACEMENT, REPAIR, AND MAINTENANCE OF OUT-OF-WARRANTY IT EQUIPMENT UNDER THE DEPED COMPUTERIZATION PROGRAM (DCP) | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-04 | NA | 2025-07-11 | 2025-07-11 | 2025-07-11 | NA | 2025-07-11 | 07/14/25 | 07/16/25 | 07/16/25 | 2025-07-23 | 2025-07-23 | OSEC-1-24-0778 | 70830 | 70830 |  | 70530 | 70530 |  | NA | NA | NA | NA | NA | NA | IAR # 20250723-001 | Completed
200000100007000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF LOCAL STAKEHOLDERS CONVERGENCE PROGRAM | SGOD | NO | Shopping | NA | 2025-07-04 | NA | 2025-07-11 | 2025-07-11 | 2025-07-11 | NA | 2025-07-11 | 07/14/25 | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | OSEC-1-25-00882 | 69990 | 69990 |  | 66990 | 66990 |  | NA | NA | NA | NA | NA | NA | IAR # 20250717-001 | Completed
310300100005000 | PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF ORIENTATION PROGRAM FOR SBFP | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-04 | NA | 2025-07-11 | 2025-07-11 | 2025-07-11 | NA | 2025-07-11 | 07/14/25 | 07/16/25 | 07/16/25 | 08/05/25 | 08/05/25 | ROI-24-0436 | 81000 | 81000 |  | 80055 | 80055 |  | NA | NA | NA | NA | NA | NA | IAR # 20250805-001 | Completed
310300100003000 | PROCUREMENT OF ADVOCACY MATERIALS (SHIRTS) TO THE PARTICIPANTS FOR THE CONDUCT OF CLUSTER ADM CONVERGENCE | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-04 | NA | 2025-07-11 | 2025-07-11 | 2025-07-11 | NA | 2025-07-11 | NA | 2025-07-18 | NA | 2025-07-25 | 2025-07-25 | ROI-25-0051 | 32500 | 32500 |  | 31200 | 31200 |  | NA | NA | NA | NA | NA | NA | IAR # 20250725-001 | Completed
200000100007000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR LEARNER FORMATION ACTIVITIES | SGOD | NO | Shopping | NA | 2025-07-04 | NA | 2025-07-11 | 2025-07-11 | 2025-07-11 | NA | 2025-07-11 | NA | 2025-07-16 | NA | 2025-07-29 | 2025-07-29 | ROI-24-0868 | 35965 | 35965 |  | 34309 | 34309 |  | NA | NA | NA | NA | NA | NA | IAR # 20250729-001 | Completed
5021300000 | PURCHASE OF WIPER BLADE AND BATTERY FOR DEPED VEHICLE (MITSUBISHI L300 PLATE NUMBER: SHV 491) | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-10 | NA | 07/17/25 | 07/17/25 | 07/17/25 | NA | 07/17/25 | NA | 2025-08-06 | NA | 2025-08-12 | 2025-08-12 | GAS MOOE 2025 | 8505 | 8505 |  | 8505 | 8505 |  | NA | NA | NA | NA | NA | NA | IAR # 20250812-003 | Completed
200000100007000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF ORIENTATION PROGRAM FOR SBFP | SGOD | NO | Shopping | NA | 2025-07-10 | NA | 07/21/25 | 07/21/25 | 07/21/25 | NA | 07/21/25 | NA | 2025-07-31 | NA | 2025-08-04 | 2025-08-04 | ROI-24-0436 | 41950 | 41950 |  | 39825.5 | 39825.5 |  | NA | NA | NA | NA | NA | NA | IAR # 20250804-001 | Completed
310300100005000 | PROCUREMENT OF CATERING SERVICES, MEALS AND SNACKS, INCLUSIVE OF TARPAULIN FOR THE CONDUCT OF DIVISION UPSKILLING AND RESKILLING OF TEACHERS ON INCLUSIVE EDUCATION | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-10 | NA | 07/17/25 | 07/17/25 | 07/17/25 | NA | 07/21/25 | 07/25/25 | 07/31/25 | 07/31/25 | 08/21/25 | 08/21/25 | ROI-25-0708 | 183600 | 183600 |  | 179928 | 179928 |  | NA | NA | NA | NA | NA | NA | IAR # 20250821-001A | Completed
310300100005000 | PROCUREMENT OF CATERING SERVICES, MEALS AND SNACKS, INCLUSIVE OF TARPAULIN FOR THE CONDUCT OF DIVISION ORIENTATION ON RA 11106 “FILIPINO SIGN LANGAUGE ACT” | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-10 | NA | 07/17/25 | 07/17/25 | 07/17/25 | NA | 07/17/25 | 07/21/25 | 07/29/25 | 07/29/25 | 08/01/2025 | 08/01/2025 | ROI-25-0708 | 100000 | 100000 |  | 97600 | 97600 |  | NA | NA | NA | NA | NA | NA | IAR # 20250801-001 | Completed
310300100005000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF DIVISION UPSKILLING AND RESKILLING OF TEACHERS ON INCLUSIVE EDUCATION | CID | NO | Shopping | NA | 2025-07-11 | NA | 07/18/25 | 07/18/25 | 07/18/25 | NA | 2025-08-08 | NA | 2025-08-12 | NA | 2025-08-12 | 2025-08-12 | ROI-25-0708 | 16398 | 16398 |  | 15202 | 15202 |  | NA | NA | NA | NA | NA | NA | IAR # 20250812-002 | Completed
310300100005000 | PROCUREMENT OF MEALS FOR ADOLESCENT REPRODUCTIVE HEALTH ORIENTATION FOR PEER HEALTH NAVIGATORS (REBID) | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 07/29/25 | NA | 2025-08-01 | 2025-08-01 | 2025-08-01 | NA | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-08-07 | 2025-05-05 | 2025-05-05 | ROI-24-1967 | 75000 | 75000 |  | 67390 | 67390 |  | NA | NA | NA | NA | NA | NA | IAR # 20250505-001 | Completed
200000100005000 | PROCUREMENT OF PRINTED INFORMATION, EDUCATION AND COMMUNICATION MATERIALS SUCH AS COFFEE TABLE MAGAZINE | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 07/18/25 | NA | 07/28/25 | 07/28/25 | 07/28/25 | NA | 07/28/25 | NA | 2025-08-04 | NA | 2025-08-22 | 2025-08-22 | ROI-25-1135 | 42000 | 42000 |  | 40500 | 40500 |  | NA | NA | NA | NA | NA | NA | IAR # 20250822-002 | Completed
310300100005000 | PROCUREMENT OF SNACKS AND LUNCH OF DIVISION CELEBRATION OF NATIONAL DISABILITY PREVENTION WEEK. | SGOD | NO |  | NA | 07/19/25 | NA | 07/28/25 | 07/28/25 | 07/28/25 | NA | 07/28/25 | NA | 2025-08-05 | NA | 10/28/25 | 10/28/25 | TRUST FUND | 6000 | 6000 |  | 6000 | 6000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251028-001 | Completed
310300100003000 | PROCUREMENT OF CATERING SERVICES, MEALS AND SNACKS, INCLUSIVE OF TARPAULIN FOR THE CONDUCT OF ORIENTATION OF SCHOOL ALTERNATIVE DELIVERY MODE (ADM) FOCAL PERSONS ON DROP-OUT REDUCTION PROGRAM (DORP) | CID | NO | NP-53.9 - Small Value Procurement | NA | 07/22/25 | NA | 07/29/25 | 07/29/25 | 07/29/25 | NA | 07/29/25 | 2025-07-30 | 2025-08-01 | 2025-08-01 | 08/14/25 | 08/14/25 | ROI-25-0900 | 61600 | 61600 |  | 58960 | 58960 |  | NA | NA | NA | NA | NA | NA | IAR # 20250814-001 | Completed
200000100007000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF ORIENTATION OF SCHOOL ALTERNATIVE DELIVERY MODE (ADM) FOCAL PERSONS ON DROP-OUT REDUCTION PROGRAM (DORP) | CID | NO | Shopping | NA | 07/22/25 | NA | 2025-08-01 | 2025-08-01 | 2025-08-01 | NA | 2025-08-01 | NA | 2025-08-06 | NA | 2025-08-12 | 2025-08-12 | ROI-25-0900 | 4398 | 4398 |  | 4192 | 4192 |  | NA | NA | NA | NA | NA | NA | IAR #- 20250812-001 | Completed
20000100006000 | PROCUREMENT OF MEALS FOR THE ART AWARENESS POSTER AND DIGITAL LOGO MAKING CONTEST | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-22 | NA | 2025-07-29 | 2025-07-29 | 2025-07-29 | NA | 2025-07-29 | NA | 2025-09-08 | NA | 11/18/25 | 11/18/25 | ROI-24-1722 | 45000 | 45000 |  | 44250 | 44250 |  | NA | NA | NA | NA | NA | NA | IAR # 20251118-001A | Completed
310400100001000 | PROCUREMENT OF GARDEN TOOLS, MATERIALS, AND EQUIPMENT (REBID) | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-08 | NA | 2025-08-14 | 2025-08-14 | 2025-08-14 | NA | 2025-08-14 | 2025-08-18 | 2025-08-19 | 2025-08-19 | 08/27/25 | 08/27/25 | ROI-25-0588 | 80000 | 80000 |  | 74300 | 74300 |  | NA | NA | NA | NA | NA | NA | IAR # 20250827-001 | Completed
310400100001000 | PROCUREMENT OF HANDWASHING SOAPS | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-07-30 | NA | 2025-08-07 | 2025-08-07 | 2025-08-07 | NA | 2025-08-07 | 2025-08-20 | 2025-08-22 | 2025-08-22 | 08/22/25 | 08/22/25 | ROI-25-0588 | 71380 | 71380 |  | 66075 | 66075 |  | NA | NA | NA | NA | NA | NA | IAR # 20250822-001 | Completed
310400100001000 | PROCUREMENT OF PASTEURIZED CARABAO’S MILK FOR THE IMPLEMENTATION OF SBFP FOR THE SY 2025-2026 | SGOD | NO | NP-Community Participation | 2025-07-15 | 2025-08-05 | NA | 2025-08-14 | 2025-08-14 | 2025-08-14 | 2025-08-18 | 2025-08-29 | 2025-09-17 | 2025-09-19 | 2025-09-23 | 10/06/25 | 10/06/25 | ROI-25-0083 | 1771875 | 1771875 |  | 1771875 | 1771875 |  | COA,FPTA,SCCTCCU | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | IAR # 20251006-002B | Completed
5021300000 | PROCUREMENT OF EGR CLEANING AND INTAKE MANIFOLD AND OTHER AUTOMOTIVE PARTS FOR DEPED DIVISION VEHICLE (MITSUBISHI STRADA PICK-UP PLATE NUMBER: 0301-1309646) | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-05 | NA | 2025-08-14 | 2025-08-14 | 2025-08-14 | NA | 2025-08-14 | NA | 2025-08-26 | NA | 09/01/25 | 09/01/25 | GAS MOOE 2025 | 11458 | 11458 |  | 11458 | 11458 |  | NA | NA | NA | NA | NA | NA | IAR # 20250901-001 | Completed
200000100001000 | PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF CAPACITY BUILDING FOR TOURNAMENT MANAGERS AND SPORTS COORDINATORS | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-08 | NA | 2025-08-18 | 2025-08-18 | 2025-08-18 | NA | 2025-08-18 | NA | 2025-08-26 | NA | 08/26/25 | 08/26/25 | OSEC-1-24-7359 | 30000 | 30000 |  | 29750 | 29750 |  | NA | NA | NA | NA | NA | NA | IAR # 20250828-002 | Completed
200000100001000 | PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF EMERGENCY RESPONSE TRAINING | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-15 | NA | 2025-08-29 | 2025-08-29 | 2025-08-29 | NA | 2025-08-29 | 2025-09-05 | 2025-09-08 | 2025-09-08 | 09/18/25 | 09/18/25 | ROI-25-0780 | 54000 | 54000 |  | 52650 | 52650 |  | NA | NA | NA | NA | NA | NA | IAR # 20250918-001 | Completed
200000100001000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF EMERGENCY RESPONSE TRAINING | SGOD | NO | Shopping | NA | 2025-08-15 | NA | 2025-08-29 | 2025-08-29 | 2025-08-29 | NA | 2025-08-29 | NA | 2025-09-09 | NA | 09/10/25 | 09/10/25 | ROI-25-0780 | 6800 | 6800 |  | 5520 | 5520 |  | NA | NA | NA | NA | NA | NA | IAR # 20250910-002 | Completed
20000100001000 | PROCUREMENT OF 1 UNIT OF PORTABLE PUBLIC ADDRESS SYSTEM AND 2 PIECES OF MICROPHONE | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-15 | NA | 2025-08-29 | 2025-08-29 | 2025-08-29 | NA | 2025-08-29 | NA | 2025-09-09 | NA | 09/15/25 | 09/15/25 | ROI-25-0316 | 49990 | 49990 |  | 45000 | 45000 |  | NA | NA | NA | NA | NA | NA | IAR # 20250915-001 | Completed
200000100001000 | PROCUREMENT OF SNACKS FOR THE PRE AND POST CONFERENCE OF DIVISION MEET 2025 (REBID) | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-02 | NA | 2025-09-09 | 2025-09-09 | 2025-09-09 | NA | 2025-09-09 | NA | 2025-10-08 | NA | 10/13/25 | 10/13/25 | OSEC-1-24-7359 | 20000 | 20000 |  | 19300 | 19300 |  | NA | NA | NA | NA | NA | NA | IAR # 20251013-003C | Completed
200000100007000 | PROCUREMENT OF SUPPLIES FOR BRIGADA ESKWELA 2025 RECOGNITION AND APPRECIATION PROGRAM | SGOD | NO | Shopping | NA | 2025-08-19 | NA | 2025-08-29 | 2025-08-29 | 2025-08-29 | NA | 2025-08-29 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 09/17/25 | 09/17/25 | OSEC-1-25-01783 | 53000 | 53000 |  | 52700 | 52700 |  | NA | NA | NA | NA | NA | NA | IAR # 20250917-001 | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN FOR THE CONDUCT OF ENHANCEMENT TRAINING ON BUILDING A CENTRALIZED IMAGE BANK FOR SELF-LEARNING MODULES | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-08-22 | NA | 2025-09-02 | 2025-09-02 | 2025-09-02 | NA | 2025-09-02 | 2025-09-05 | 2025-09-11 | 2025-09-11 | 10/09/25 | 10/09/25 | ROI-24-1076 | 180000 | 180000 |  | 178380 | 178380 |  | NA | NA | NA | NA | NA | NA | IAR # 20251009-001A | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF EQUIPMENT FOR THE CONDUCT OF ENHANCEMENT TRAINING ON BUILDING A CENTRALIZED IMAGE BANK FOR SELF-LEARNING MODULES (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-04 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | 2025-09-16 | 2025-09-19 | 2025-09-19 | 09/23/25 | 09/23/25 | ROI-24-1076 | 144000 | 144000 |  | 138400 | 138400 |  | NA | NA | NA | NA | NA | NA | IAR # 20250923-001 | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF ENHANCEMENT TRAINING ON BUILDING A CENTRALIZED IMAGE BANK FOR SELF-LEARNING MODULES | CID | NO | Shopping | NA | 2025-08-22 | NA | 2025-09-02 | 2025-09-02 | 2025-09-02 | NA | 2025-09-02 | NA | 2025-09-09 | NA | 09/10/25 | 09/10/25 | ROI-24-1076 | 5874 | 5874 |  | 5314 | 5314 |  | NA | NA | NA | NA | NA | NA | IAR # 20250910-001 | Completed
310500100001000 | PROCUREMENT OF CATERING SERVICES, MEALS AND SNACKS FOR THE CONDUCT OF THE CAPACITY BUILDING FOR CAREER GUIDANCE ADVOCATES ON THE IMPLEMENTATION OF CAREER GUIDANCE PROGRAM | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-02 | NA | 2025-09-09 | 2025-09-09 | 2025-09-09 | NA | 2025-09-09 | 2025-09-09 | 2025-09-09 | 2025-09-09 | 09/24/25 | 09/24/25 | ROI-25-1408 | 288000 | 288000 |  | 280800 | 280800 |  | NA | NA | NA | NA | NA | NA | IAR # 20250924-002A | Completed
200000100001000 | PROCUREMENT OF SPORTS APPAREL / UNIFORM FOR TOURNAMENT MANAGERS, OFFICIALS AND TECHNICAL WORKING GROUP | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-02 | NA | 2025-09-09 | 2025-09-09 | 2025-09-09 | NA | 2025-09-09 | NA | 2025-09-23 | NA | 09/29/25 | 09/29/25 | OSEC-1-24-7359 | 39900 | 39900 |  | 35000 | 35000 |  | NA | NA | NA | NA | NA | NA | IAR # 20250929-001 | Completed
310300100005000 | PROCUREMENT OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN ON THE CONDUCT OF TRAINING OF TEACHERS ON BEHAVIORAL AND SPEECH THERAPY IN HANDLING LEARNERS WITH DISABILITIES | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-16 | 2025-09-16 | 2025-09-16 | NA | 2025-09-16 | 2025-09-16 | 2025-09-19 | 2025-09-19 | 09/18/25 | 09/18/25 | ROI-25-0259 | 70200 | 70200 |  | 70083 | 70083 |  | NA | NA | NA | NA | NA | NA | IAR # 20250918-002A | Completed
310300100005000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF TRAINING OF TEACHERS ON BEHAVIORAL THERAPY IN HANDLING LEARNERS WITH DISABILITIES | CID | NO | Shopping | NA | 2025-09-09 | NA | 2025-09-16 | 2025-09-16 | 2025-09-16 | NA | 2025-09-16 | NA | 2025-09-19 | NA | 09/13/25 | 09/13/25 | ROI-25-0259 | 4800 | 4800 |  | 3665 | 3665 |  | NA | NA | NA | NA | NA | NA | IAR # 20250913-001 | Completed
310300100005000 | PROCUREMENT OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN, VENUE AND ACCOMMODATION FOR THE ORIENTATION WORKSHOP OF CORE TRAINERS ON SNED (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-16 | NA | 2025-09-23 | 2025-09-23 | 2025-09-23 | NA | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 11/18/25 | 11/18/25 | ROI-25-0259 | 180000 | 180000 |  | 180000 | 180000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251118-003C | Completed
310300100005000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE ORIENTATION WORKSHOP OF CORE TRAINERS ON SNED ANALYSIS AND UTILIZATION OF DATA IN THE DEVELOPMENT OF RESEARCH AND INNOVATION | CID | NO | Shopping | NA | 2025-09-09 | NA | 2025-09-16 | 2025-09-16 | 2025-09-16 | NA | 2025-09-16 | NA | 2025-09-23 | NA | 09/26/25 | 09/26/25 | ROI-25-0259 | 4998 | 4998 |  | 4748 | 4748 |  | NA | NA | NA | NA | NA | NA | IAR # 20250926-001 | Completed
310500100001000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF THE CAPACITY BUILDING FOR CAREER GUIDANCE ADVOCATES ON THE IMPLEMENTATION OF CAREER GUIDANCE PROGRAM | SGOD | NO | Shopping | NA | 2025-09-09 | NA | 2025-09-23 | 2025-09-23 | 2025-09-23 | NA | 2025-09-23 | NA | 2025-09-24 | NA | 09/24/25 | 09/24/25 | ROI-25-1408 | 10295 | 10295 |  | 8115 | 8115 |  | NA | NA | NA | NA | NA | NA | IAR # 20250924-001 | Completed
310100100003000 | PROCUREMENT OF SNACKS FOR THE REGIONAL LAUNCHING OF ARAL PROGRAM (FOR PARTICIPANTS) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-12 | NA | 09/13/25 | 09/13/25 | ROI-25-1047 | 32000 | 32000 |  | 32000 | 32000 |  | NA | NA | NA | NA | NA | NA | IAR # 2025-0913-002A | Completed
310100100003000 | PROCUREMENT OF MEALS FOR THE REGIONAL LAUNCHING OF ARAL PROGRAM (FOR TWG AND HOST DIVISION PERSONNEL) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-13 | NA | 09/13/25 | 09/13/25 | ROI-25-1047 | 16740 | 16740 |  | 16740 | 16740 |  | NA | NA | NA | NA | NA | NA | IAR # 20250913-004A | Completed
310100100003000 | PROCUREMENT OF ARAL SHIRTS FOR THE PARTICIPANTS OF THE REGIONAL LAUNCHING OF ARAL PROGRAM | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-12 | NA | 09/13/25 | 09/13/25 | ROI-25-1047 | 49850 | 49850 |  | 49850 | 49850 |  | NA | NA | NA | NA | NA | NA | IAR # 20250913-001 | Completed
310100100003000 | PRINTING AND LAYOUT OF THE STAGE BACKDROP (TARPAULIN) FOR THE REGIONAL LAUNCHING OF ARAL PROGRAM | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-12 | NA | 09/12/2025 | 09/12/2025 | ROI-25-1047 | 3000 | 3000 |  | 3000 | 3000 |  | NA | NA | NA | NA | NA | NA | IAR # 20250912-002 | Completed
310100100003000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR THE REGIONAL LAUCHING OF ARAL PROGRAM | CID | NO | Shopping | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-12 | NA | 09/12/2025 | 09/12/2025 | ROI-25-1047 | 14370 | 14370 |  | 14370 | 14370 |  | NA | NA | NA | NA | NA | NA | IAR # 20250912-001 | Completed
310100100003000 | PROCUREMENT OF MEALS FOR THE REGIONAL LAUNCHING OF ARAL PROGRAM (FOR GUESTS/OFFICIALS) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-09 | NA | 2025-09-11 | 2025-09-11 | 2025-09-11 | NA | 2025-09-11 | NA | 2025-09-13 | NA | 09/13/25 | 09/13/25 | ROI-25-1047 | 19600 | 19600 |  | 19600 | 19600 |  | NA | NA | NA | NA | NA | NA | IAR # 20250913-002A | Completed
310200100004000 | DC15-PROCUREMENT AND DELIVERY OF SUPPLEMENTARY LEARNING RESOURCES FOR THE SCHOOL LIBRARIES OF MAGTAKING ES and SEPNAS | CID | NO | Direct Contracting | NA | 2025-09-24 | NA | 2025-10-10 | 2025-10-10 | 2025-10-10 | NA | 2025-10-10 |  | 2025-11-24 | 2025-11-24 | 12/04/25 | 12/04/25 | ROI-25-0470 | 66596 | 66596 |  | 66596 | 66596 |  | NA | NA | NA | NA | NA | NA | IAR # 20251204-001 | Completed
5020200000 | SUPPLY OF LUNCH FOR THE CONDUCT OF 2025 WORLD TEACHERS’ DAY ON OCTOBER 2, 2025 | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-09-26 | NA | 2025-09-30 | 2025-09-30 | 2025-09-30 | NA | 2025-09-30 | 2025-09-30 | 2025-10-01 | 2025-10-01 | 10/02/25 | 10/02/25 | GAS MOOE 2025 | 68000 | 68000 |  | 68000 | 68000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251002-001 | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN FOR THE PHASE 2 FINALIZATION OF THE COMPUTER SYSTEMS SERVICING (CSS) 1ST AND 2ND QUARTERS SELF-LEARNING MODULES (SLMS) FOR STRENGTHENED SENIOR HIGH SCHOOL CURRICULUM (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-16 | NA | 2025-10-20 | 2025-10-20 | 2025-10-20 | NA | 2025-10-20 | 2025-10-20 | 2025-10-27 | 2025-10-27 | 11/24/25 | 11/24/25 | ROI-25-0648 | 108000 | 108000 |  | 107940 | 107940 |  | NA | NA | NA | NA | NA | NA | IAR # 20251124-001 | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF MEALS AND SNACKS INCLUSIVE OF TARPAULIN FOR THE PHASE 1 DEVELOPMENT OF THE COMPUTER SYSTEMS SERVICING (CSS) 1ST AND 2ND QUARTERS SELF-LEARNING MODULES (SLMs) FOR STRENGTHENED SENIOR HIGH SCHOOL CURRICULUM (REBID) | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-16 | NA | 2025-10-20 | 2025-10-20 | 2025-10-20 | NA | 2025-10-20 | NA | 2025-10-27 | NA | 11/18/25 | 11/18/25 | ROI-25-0648 | 43200 | 43200 |  | 43164 | 43164 |  | NA | NA | NA | NA | NA | NA | IAR # 20251118-002B | Completed
310300100003000 | PROCUREMENT AND DELIVERY OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF DEVELOPMENT AND FINALIZATION OF THE COMPUTER SYSTEMS SERVICING (CSS) 1ST AND 2ND QUARTERS SELF-LEARNING MODULES (SLMS) FOR STRENGTHENED SENIOR HIGH SCHOOL CURRICULUM | CID | NO | Shopping | NA | 2025-10-06 | NA | 2025-10-20 | 2025-10-20 | 2025-10-20 | NA | 2025-10-20 | NA | 2025-10-02 | NA | 10/24/25 | 10/24/25 | ROI-25-0648 | 7202 | 7202 |  | 6472.5 | 6472.5 |  | NA | NA | NA | NA | NA | NA | IAR # 20251024-001 | Completed
5021300000 | PERIODIC MAINTENANCE AND REPAIR OF AIR-CONDITIONING UNITS AT THE DIVISION OFFICE | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-06 | NA | 2025-10-16 | 2025-10-16 | 2025-10-16 | NA | 2025-10-16 | 2025-10-16 | 2025-11-04 | 2025-11-04 | 2025-11-11 | 2025-11-11 | GAS MOOE 2025 | 52750 | 52750 |  | 51850 | 51850 |  | NA | NA | NA | NA | NA | NA | IAR # 20251111-001 | Completed
100000100001000 | SUPPLY AND DELIVERY OF FURNITURE AND FIXTURES FOR DIVISION OFFICE OF SDO - SCC | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-06 | NA | 2025-10-16 | 2025-10-16 | 2025-10-16 | NA | 2025-10-16 | 2025-10-16 | 2025-11-07 | 2025-11-07 | 11/14/25 | 11/14/25 | OSEC-1-25-04226 | 67500 | 67500 |  | 58500 | 58500 |  | NA | NA | NA | NA | NA | NA | IAR # 20251114-002 | Completed
100000100001000 | SUPPLY AND DELIVERY OF OFFICE EQUIPMENT FOR DIVISION OFFICE OF SDO - SCC | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-06 | NA | 2025-10-16 | 2025-10-16 | 2025-10-16 | NA | 2025-10-16 | NA | 2025-11-07 | NA | 11/14/25 | 11/14/25 | OSEC-1-25-04226 | 20100 | 20100 |  | 18000 | 18000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251114-001 | Completed
310500100001000 | PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF THE HUMAN RESOURCE MERIT PROMOTION AND SELECTION BOARD (HRMPSB) ASSESSORS TRAINING: DEEPENING ON INITIAL EVALUATION AND PPST ASSESSMENT | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 09/10/2025 | NA | 10/13/25 | 10/13/25 | N/A | NA | 10/13/25 | 10/14/25 | 2025-10-14 | 10/14/25 | 10/14/25 | 10/14/25 | RO1-25-0662 | 108000 | 108000 |  | 106650 | 106650 |  | NA | NA | NA | NA | NA | NA | IAR # 20251014-001 | Completed
310100100003000 | REPRODUCTION AND DELIVERY OF THE ARAL LEARNING RESOURCES | CID | NO | NP-53.9 - Small Value Procurement | NA | 2025-10-06 | NA | 2025-10-20 | 2025-10-20 | 2025-10-20 | NA | 2025-10-20 | 2025-10-20 | 2025-11-04 | 2025-11-04 | 10/11/2025 | 10/11/2025 | ROI-25-1047 | 325230.6 | 325230.6 |  | 270071.9 | 270071.9 |  | NA | NA | NA | NA | NA | NA | IAR # 20251011-001 | Completed
200000100006000 | PROCUREMENT OF SUPPLIES AND MATERIALS AND EQUIPMENT (REBID) | SGOD | NO | Shopping | NA | 11/26/25 | NA | 12/03/25 | 12/03/25 | NA | NA | 12/03/2025 | 12/03/25 | 2025-12-17 | 2025-12-17 | 12/19/25 | 12/19/25 | ROI-24-1722 | 58000 | 58000 |  | 53380 | 53380 |  | NA | NA | NA | NA | NA | NA | IAR # 20251219-001 | Completed
200000100006000 | PROCUREMENT OF PRIZES FOR DIGITAL LOGO MAKING CONTEST | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 11/06/25 | N/A | 11/14/25 | 11/14/25 | N/A | N/A | 11/14/25 | N/A | 11/17/25 | N/A | 11/18/25 | 11/18/25 | ROI-24-1722 | 21340 | 21340 |  | 21000 | 21000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251118-004D | Completed
200000100012000 | PROCUREMENT OF MEALS AND ACCOMMODATION FOR THE CONDUCT OF ENHANCING ADMINISTRATIVE EXCELLENCE THROUGH EFFECTIVE COMMUNICATION SKILLS, WORK EFFICIENCY AND ETHICAL DECISION-MAKING | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 2025-11-12 | NA | 11/20/25 | 11/20/25 | N/A | N/A | 11/21/25 | 11/26/25 | 11/26/25 | 11/27/25 | 11/28/25 | 11/28/25 11/29/25 | RO1-25-2330 | 280000 | 280000 |  | 279300 | 279300 |  | NA | NA | NA | NA | NA | NA | IAR # 20251128-001A | Completed
310400100001000 | PROCUREMENT OF IEC MATERIALS FOR THE PROMOTION ON HEALTH AND WELLNESS PROGRAM | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 11/04/25 | NA | 2025-11-11 | 2025-11-11 | N/A | N/A | 2025-11-11 | N/A | 2025-11-18 | N/A | 11/25/25 | 11/25/25 | RO1-24-1953 | 49999.04 | 49999.04 |  | 41208 | 41208 |  | NA | NA | NA | NA | NA | NA | IAR # 20251125-002 | Completed
100000100001000 | PURCHASE AND INSTALLATION OF TIRES FOR DEPED VEHICLE MITSUBISHI STRADA PICKUP PLATE NO. 0301-1309646 | OSDS | NO | NP-53.9 - Small Value Procurement | NA | 10/27/25 | N/A | 11/04/25 | 11/04/25 | N/A | NA | 2025-04-11 | N/A | 2025-11-20 | N/A | 11/27/25 | 11/27/25 | GAA MOOE 2025 | 43974 | 43974 |  | 43974 | 43974 |  | NA | NA | NA | NA | NA | NA | IAR # 20251127-002 | Completed
310100100001000 | PROCUREMENT AND DELIVERY OF SUPPLIES AND MATERIALS FOR THE PRINTING OF ALS FORMS FOR THE IMPLEMENTATION OF ALS PROGRAM | CID | NO | Shopping | NA | 10/30/25 | N/A | 2025-07-11 | 2025-07-11 | N/A | NA | 2025-07-11 | N/A | 2025-11-24 | N/A | 11/25/25 | 11/25/25 | RO1-25-0273 | 17100 | 17100 |  | 13765 | 13765 |  | NA | NA | NA | NA | NA | NA | IAR # 20251125-001 | Completed
310100100001000 | PROCUREMENT AND DELIVERY OF MATERIALS FOR THE IMPLEMENTATION OF ALS PROGRAMS AND PROJECTS | CID | NO | NP-53.9 - Small Value Procurement | NA | 11/06/25 | N/A | 11/13/25 | 11/13/25 | N/A | NA | 11/13/25 | N/A | 2025-11-24 | N/A | 11/27/25 | 11/27/25 | RO1-24-1409 | 21903.9 | 21903.9 |  | 21700 | 21700 |  | NA | NA | NA | NA | NA | NA | IAR # 20251127-001 | Completed
100000100001000 | SUPPLY AND DELIVERY OF SUPPLIES AND EQUIPMENT FOR THE 2ND SEMESTER OF FY 2025 FOR SDO SCC | OSDS | NO | Shopping | NA | 11/19/25 | N/A | 12/03/25 | 12/03/25 | N/A | NA | 12/03/25 | 12/03/25 | 2025-12-16 | 2025-12-16 | ONGOING | ONGOING | GAS MOOE 2025 | 245312.5 | 245312.5 |  | 217377 | 217377 |  | NA | NA | NA | NA | NA | NA | IAR # 20251215-001 | Completed
310400100001000 | PROCUREMENT OF OFFICE SUPPLIES AND MATERIALS FOR THE IMPLEMENTATION OF GPP | SGOD | NO | Shopping | N/A | 11/14/25 | N/A | 11/20/25 | 11/20/25 | N/A | N/A | 11/21/25 | N/A | 2025-12-17 | N/A | 12/18/25 | 12/18/25 | RO1-25-0588 | 19905 | 19905 |  | 18660 | 18660 |  | NA | NA | NA | NA | NA | NA | IAR # 20251218-001 | Completed
5020200000 | GADKILOS 2025: GENDER AWARENESS AND DEVELOPMENT FOR KNOWLEDGE, INCLUSION, LEADERSHIP, AND OPPORTUNITIES FOR SERVANT-LEADERS | SGOD | NO | NP-Agency to Agency | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 08/12/25 | 10/11/25 | 10/11/25 | 10/11/25 10/12/25 | N/A | GAA MOOE 2025 | 225000 | 225000 |  | 225000 | 225000 |  | NA | NA | NA | NA | NA | NA | N/A | Completed
310100100007000 | PROCUREMENT OF SUPPLIES FOR THE ONE-DAY DIVISION ORIENTATION OF SCHOOL HEAD ON THE SCIENCE OF READING (REBID) | CID | NO | Shopping | N/A | 12/04/25 | N/A | 12/09/25 | 12/09/25 | N/A | N/A | 2025-09-12 | N/A | 2025-12-19 | N/A | 12/22/25 | 12/22/25 | RO1-25-1312 | 990 | 990 |  | 628 | 628 |  | NA | NA | NA | NA | NA | NA | IAR # 20251226-001 | Completed
5020200000 | SUPPLY OF SNACKS AND MEALS FOR THE CONDUCT OF YEAR-END GENDER AND DEVELOPMENT (GAD) LEARNING AND WELLNESS CULMINATING ACTIVITY | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/10/25 | N/A | 12/19/25 | 12/19/25 | N/A | N/A | 12/19/25 | 12/19/25 | 2025-12-19 | 2025-12-19 | 12/22/25 | 12/22/25 | GASS 2025 MOOE | 160000 | 160000 |  | 160000 | 160000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251222-001A | Completed
5020200000 | DELIVERY OF SUPPLIES AND MATERIALS FOR THE CONDUCT OF YEAR-END GENDER AND DEVELOPMENT (GAD) LEARNING AND WELLNESS CULMINATING ACTIVITY | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/10/25 | N/A | 11/25/2025 | 11/25/25 | N/A | N/A | 11/25/25 | N/A | 2025-12-19 | N/A | 12/22/25 | 12/22/25 | GASS 2025 MOOE | 9000 | 9000 |  | 8005 | 8005 |  | NA | NA | NA | NA | NA | NA | IAR # 20251222-002 | Completed
200000100006000 | PROCUREMENT AND DELIVERY OF MEALS AND SNACKS FOR THE JOINT DIVISION CELEBRATION OF NATIONAL CHILDRENS MONTH & NATIONALSTUDENT'S DAY | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 11/06/25 | N/A | 11/13/25 | 11/13/25 | N/A | N/A | 11/13/25 | 11/13/25 | 11/18/25 | 11/18/25 | 11/18/25 | 11/18/25 | RO1-25-1494 | 120000 | 120000 |  | 117000 | 117000 |  | NA | NA | NA | NA | NA | NA | IAR # 20251118-003D | Completed
200000100011000 | PROCUREMENT AND DELIVERY OF FIRE EXTINGUISHERS (SOURCE OF FUND: ROI-25-0316) | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/06/25 | N/A | 12/16/25 | 12/16/25 | N/A | N/A | 12/16/25 | N/A | 2025-12-23 | N/A | ONGOING | ONGOING | RO1-25-0316 | 5000 | 5000 |  | 4480 | 4480 |  | NA | NA | NA | NA | NA | NA | IAR # 20251226-003 | Completed
200000100011000 | PROCUREMENT AND DELIVERY OF FIRE EXTINGUISHERS (SOURCE OF FUND: ROI-24-0973) | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/06/25 | N/A | 12/16/25 | 12/16/25 | N/A | N/A | 12/16/25 | N/A | 2025-12-23 | N/A | ONGOING | ONGOING | RO1-24-0973 | 12500 | 12500 |  | 11200 | 11200 |  | NA | NA | NA | NA | NA | NA | IAR # 20251226-002 | Completed
310400100001000 | PROCUREMENT OF PASTEURIZED CARABAO’S MILK FOR THE IMPLEMENTATION OF SBFP FOR THE SY 2025-2026 (SUPPLEMENTAL FEEDING) (REBID) | SGOD | NO | NP-Community Participation | 10/20/25 | 11/26/25 | N/A | 12/10/25 | 12/10/25 | N/A | N/A | 2025-12-12 | 2025-12-12 | 12/22/25 | 12/22/25 | 01/05/26 | 01/05/26 | ROI-24-0101 | 472500 | 472500 |  | 471375 | 471375 |  | COA,FPTA,SCCTCCU | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | IAR # 20260105-002b | Completed
310400100001000 | PROCUREMENT OF MEDICINES FOR THE IMPLEMENTATION OF SBFP | SGOD | NO | Competitive Bidding | 10/20/25 | 2025-10-25 | 11/03/25 | 11/17/25 | 11/17/25 | 11/18/25 11/19/25 | 11/18/25 11/19/25 | 2025-11-19 | 2025-12-01 | 2025-12-08 | 2025-12-09 | 2025-12-12 | 2025-12-12 | ROI-24-0101 | 87185.2 | 87185.2 |  | 87134 | 87134 |  | COA,FPTA,SCCTCCU | 10/28/25 | 10/28/25 | 10/28/25 | 10/28/25 | 10/28/25 | IAR # 20251212-002 | Completed
30100100003000 | REPRODUCTION AND DELIVERY OF THE ARAL LEARNING RESOURCES | CID | NO | Competitive Bidding | 09/24/25 | 10/08/25 | 10/16/25 | 10/29/25 | 10/29/25 | 10/30/25 10/31/25 | 10/30/25 10/31/25 | 2025-11-17 | 2025-11-20 | 2025-11-28 | 2025-12-01 | 2025-12-12 | 2025-12-12 | RO1-25-1799 | 498768 | 498768 |  | 407186.26 | 407186.26 |  | COA,FPTA,SCCTCCU | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | IAR # 20251212-001 | Completed
310500100001000 | PROCUREMENT OF SUPPLIES AND EQUIPMENT IN THE CONDUCT OF DIVISION-CSC PRAISE AWARDING CEREMONY (REBID) | SGOD | NO | Competitive Bidding | 2025-05-08 | 10/11/2025 | 10/20/25 | 11/03/25 | 11/03/25 | 11/04/25 11/05/25 | 11/03/25 | 11/07/2025 | 11/17/25 | 2025-11-19 | 2025-11-20 | 12/04/25 | 12/04/25 | HRD GAA 2024 | 55800 | 55800 |  | 55700 | 55700 |  | COA,FPTA,SCCTCCU | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | IAR # 20251204-001 | Completed
310500100001000 | PROCUREMENT OF MEALS WITH PROVISION OF TRAINING VENUE AND ACCOMMODATION OF RESOURCE SPEAKERS ONLY FOR THE CONDUCT OF DIVISION TRAINING WORKSHOP ON THE DEVELOPMENT AND INTEGRATION OF PISA-LIKE QUESTIONS IN ENGLISH, SCIENCE, AND MATHEMATICS FOR GRADE 5 & 6 TEACHERS (REBID) | SGOD | NO | NP-53.1-TFB | 06/03/2025 | 10/14/25 | 10/22/25 | 10/23/25 | 10/23/25 | 10/24/25 10/27/25 | 10/24/25 10/27/25 | 2025-10-27 | 2025-11-03 | 2025-11-18 | 2025-11-18 | 11/25/25 | 11/25/25 | RO1-25-0474 | 749200 | 749200 |  | 730000 | 730000 |  | COA,FPTA,SCCTCCU | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | IAR # 20251125-001A | Completed
310500100001000 | PROCUREMENT OF TRAINING SUPPLIES AND MATERIALS FOR THE CONDUCT OF DIVISION TRAINING-WORKSHOP ON THE DEVELOPMENT AND INTEGRATION OF PISA-LIKE QUESTIONS IN ENGLISH, SCIENCE, AND MATHEMATICS FOR GRADE 5 & 6 TEACHERS | SGOD | NO | NP-53.1-TFB | 06/03/25 | 09/17/25 | 09/25/25 | 10/01/25 | 10/01/25 | 10/2/25 | 10/2/25 | 10/3/25 | 2025-10-09 | 2025-10-15 | 2025-10-16 | 10/20/25 | 10/20/25 | RO1-25-0474 | 47992 | 47992 |  | 47942 | 47942 |  | COA,FPTA,SCCTCCU | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | 10/15/25 | IAR # 20251020-001 | Completed
310200100006000 | REPAIR AND REHABILITATION OF PRINCIPAL’S OFFICE | SGOD | NO | Competitive Bidding | 07/08/25 | 2025-07-15 | 07/29/25 | 2025-08-11 | 2025-08-11 | 2025-08-11 | 2025-08-14 | 2025-08-29 | 2025-09-02 | 2025-09-12 | 2025-09-18 | 11/17/25 | 11/17/25 | OSEC-1-24-5396 | 668799.92 | 668799.92 |  | 668618.31 | 668618.31 |  | COA,FPTA,SCCTCCU | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | 2025-07-17 | Acceptance report | Completed
310400100001000 | PROCUREMENT OF NUTRITIOUS FOOD PRODUCTS FOR THE IMPLEMENTATION OF SBFP FOR SY 2025-2026 “LOT D- PROCUREMENT OF RICE- MONGO CURLS + FRUIT JUICE” (REBID) | SGOD | NO | Competitive Bidding | 04/21/25 | 06/14/25 | 06/23/25 | 2025-07-07 | 2025-07-07 | 2025-07-07 | 07/08/25 | 2025-07-31 | 2025-08-05 | 2025-08-19 | 2025-08-20 | 11/03/25 | 11/03/25 | RO1-25-0083 | 3144240 | 3144240 |  | 3001320 | 3001320 |  | COA,FPTA,SCCTCCU | 06/18/25 | 06/18/25 | 06/18/25 | 06/18/25 | 06/18/25 | IAR # 20251103-002B | Completed
310500100001000 | (BOARD AND LODGING AND MEALS) PROCUREMENT OF BOARD AND LODGING AND MEALS FOR PLANNING WORKSHOP ON SGOD EFFECTIVE STRATEGIES QUALITY MANAGEMENT AND COMMUNITY COLLABORATION (REBID) | SGOD | NO | NP-53.1-TFB | 03/10/25 | 08/23/25 | 09/01/25 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-09-05 | 2025-09-12 | 2025-09-16 | 2025-09-17 | 09/29/25 | 09/29/25 | HRD GAA 2024 | 494000 | 494000 |  | 493905 | 493905 |  | COA,FPTA,SCCTCCU | 08/27/25 | 08/27/25 | 08/27/25 | 08/27/25 | 08/27/25 | IAR # 20250929-003C | Completed
310500100001000 | (BOARD AND LODGING AND MEALS) PROCUREMENT OF BOARD AND LODGING AND MEALS FOR THE NATIONAL READING PROGRAM TRAINING WORKSHOP (REBID) | SGOD | NO | NP-53.1-TFB | 03/10/25 | 08/23/25 | 09/01/25 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-03 | 2025-09-05 | 2025-09-16 | 2025-09-17 | 2025-09-17 | 09/22/25 | 09/22/25 | HRD GAA 2024 | 478400 | 478400 |  | 450000 | 450000 |  | COA,FPTA,SCCTCCU | 08/27/25 | 08/27/25 | 08/27/25 | 08/27/25 | 08/27/25 | IAR # 20250922-001A | Completed
310500100001000 | PROCUREMENT OF TRAINING SUPPLIES FOR VARIOUS HRD RELATED ACTIVITIES (REBID) | SGOD | NO | Competitive Bidding | 07//21/25 | 2025-08-19 | 08/27/25 | 2025-09-09 | 2025-09-09 | 09/10/25 09/11/25 | 09/10/25 09/11/25 | 2025-09-11 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 09/19/25 09/30/25 | 09/19/25 09/30/25 | GAA 2024 | 165800 | 165800 |  | 165730 | 165730 |  | COA,FPTA,SCCTCCU | 08/19/25 | 08/19/25 | 08/19/25 | 08/19/25 | 08/19/25 | IAR # 20250919-001/20250930-001 | Completed
310200100004000 | PRODUCTION AND DELIVERY OF TRANSITION LEARNING RESOURCES (LESSON EXEMPLARS AND LEARNING ACTIVITY SHEETS) FOR THE IMPLEMENTATION OF THE MATATAG CURRICULUM FOR GRADE 8, 1st to 4th QUARTERS | CID | NO | Competitive Bidding | 07/14/25 | 08/05/25 | 2025-08-13 | 2025-08-26 | 2025-08-26 | 2025-11-09 | 08/27/25 08/28/25 | 2025-09-03 | 2025-09-04 | 2025-09-10 | 2025-09-11 | 10/01/25 | 10/01/25 | RO1- 25-0868 | 817462.8 | 817462.8 |  | 808600 | 808600 |  | COA,FPTA,SCCTCCU | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | IAR #2 20251001-002 | Completed
310200100004000 | PRODUCTION AND DELIVERY OF TRANSITION LEARNING RESOURCES (LESSON EXEMPLARS AND LEARNING ACTIVITY SHEETS) FOR THE IMPLEMENTATION FOR THE MATATAG CURRICULUM OF GRADES 2 AND 3, 1st AND 2nd QUARTERS | CID | NO | Competitive Bidding | 07/14/25 | 08/05/25 | 2025-08-13 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 08/27/25 08/28/25 | 2025-09-03 | 2025-09-04 | 2025-09-10 | 2025-09-10 | 10/15/25 | 10/15/25 | RO1- 25-0868 | 410293.2 | 410293.2 |  | 369263.88 | 369263.88 |  | COA,FPTA,SCCTCCU | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | IAR # 20251015-001 | Completed
310200100004000 | PRODUCTION AND DELIVERY OF TRANSITION LEARNING RESOURCES (LESSON EXEMPLARS AND LEARNING ACTIVITY SHEETS) FOR THE IMPLEMENTATION OF THE MATATAG CURRICULUM FOR GRADE 5, 1st to 4th QUARTERS | CID | NO | Competitive Bidding | 07/14/25 | 08/05/25 | 2025-08-13 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 08/27/25 08/28/25 | 2025-09-03 | 2025-09-04 | 2025-09-10 | 2025-09-10 | 10/01/2025 | 10/01/2025 | RO1- 25-0868 | 970320 | 970320 |  | 681219 | 681219 |  | COA,FPTA,SCCTCCU | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | 2025-08-08 | IAR # 20251001-002 | Completed
310500100001000 | PROCUREMENT OF CATERING SERVICES FOR THE CONDUCT OF DIVISION TRAINING OF TEACHERS ON THE IMPLEMENTATION OF THE REVISED K TO 12 CURRICULUM FOR GRADES 2,3,5 AND 8 (REBID) | SGOD | NO | Competitive Bidding | 06/13/.25 | 07/30/25 | 08/07/25 | 2025-08-20 | 2025-08-20 | 08/20/25 | 2025-08-21 | 2025-08-22 | 2025-08-22 | 2025-08-29 | 2025-08-29 | 09/04/25 09/05/25 09/06/25 | 2025-09-09 | RO1-25-0794 | 1170000 | 1170000 |  | 1166100 | 1166100 |  | COA,FPTA,SCCTCCU | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | IAR #20250904-001 | Completed
310500100001000 | PROCUREMENT OF TRAINING SUPPLIES FOR THE CONDUCT OF TRAINING OF TEACHERS ON THE IMPLEMENTATION OF THE REVISED K TO 12 CURRICULUM FOR GRADE 2,3,5 & 8 (REBID) | SGOD | NO | Competitive Bidding | 06/13/25 | 07/30/25 | 08/07/25 | 2025-08-20 | 2025-08-20 | 08/20/25 | 2025-08-21 | 2025-08-22 | 2025-08-22 | 2025-08-26 | 2025-08-26 | 08/29/25 | 08/29/25 | RO1-25-0794 | 123300 | 123300 |  | 123000 | 123000 |  | COA,FPTA,SCCTCCU | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | 08/13/25 | IAR # 20250829-001 | Completed
310100100003000 | PRODUCTION AND DELIVERY OF TRANSITION LEARNING RESOURCES OF GRADE 1 QUARTER 3 LESSON EXEMPLARS AND LEARNING ACTIVITY SHEETS (WORKSHEETS) FOR THE IMPLEMENTATION OF THE MATATAG CURRICULUM | CID | NO | NP-53.1-TFB | 06/25/25 | 07/19/25 | 07/24/25 | 07/28/25 | 07/28/25 | 07/28/25 | 07/29/25 | 2025-07-29 | 2025-08-05 | 2025-08-13 | 2025-08-13 | 08/18/25 | 08/18/25 | RO1-24-1194 | 54676.5 | 54676.5 |  | 53780.25 | 53780.25 |  | COA,FPTA,SCCTCCU | 07/18/25 | 07/18/25 | 07/18/25 | 07/18/25 | 07/18/25 | IAR # 20250818-001 | Completed
Total Alloted Budget of Procurement Activities | [17 empty] | 17189701.66
Total Contract Price of Procurement Actitvites Conducted | [17 empty] | 16359219.6
Total Savings (Total Alloted Budget - Total Contract Price) | [17 empty] | 830482.06
ONGOING PROCUREMENT ACTIVITIES
5021203000 | PROCUREMENT OF SECURITY SERVICES FOR SCHOOLS DIVISION OFFICE OF SAN CARLOS CITY, PANGASINAN FOR FY 2026 (REBID) | OSDS | YES | Competitive Bidding | 10/20/25 | 2025-12-02 | 2025-12-10 | 12/23/25 | 12/23/25 | 12/23/25 | 12/23/25 | ONGOING | ONGOING | ONGOING | ONGOING | ONGOING | ONGOING | GAAS MOOE 2026 | 369600 | 369600 |  | 369600 | 369600 |  | COA,FPTA,SCCTCCU | 11/12/25 | 11/12/25 | 11/12/25 | 11/12/25 | 11/12/25 | ONGOING | ONGOING
310400100001000 | PROCUREMENT OF NUTRITIOUS FOOD PRODUCTS FOR THE IMPLEMENTATION OF SBFP FOR SY 2025-2026“LOT B- PROCUREMENT OF IRON-FORTIFIED RICE (IFR) | SGOD | NO | NP-53.1-TFB | 04/21/25 | 10/09/25 | 10/17/25 | 10/23/25 | 10/23/25 | 10/24/25 10/27/25 | 10/24/25 10/27/25 | 2025-11-07 | 2025-11-18 | 11/26/25 | 11/26/25 | 12/01/25 | 12/01/25 | RO1-25-0083 | 1572120 | 1572120 |  | 1571405.4 | 1571405.4 |  | COA,FPTA,SCCTCCU | 1'0/09/25 | 1'0/09/25 | 1'0/09/25 | 1'0/09/25 | 1'0/09/25 | IAR # 20251201-002B | ONGOING
310400100001000 | PROCUREMENT OF NUTRITIOUS FOOD PRODUCTS FOR THE IMPLEMENTATION OF SBFP FOR SY 2025-2026 “LOT C- PROCUREMENT OF BROWN RICE NUTTY FRUITY BAR | SGOD | NO | NP-53.1-TFB | 04/21/25 | 10/09/25 | 10/17/25 | 10/23/25 | 10/23/25 | 10/24/25 | 10/24/25 | 2025-11-07 | 2025-11-18 | 2025-11-27 | 2025-11-27 | 2025-01-12 | 2025-01-12 | RO1-25-0083 | 3001320 | 3001320 |  | 2685180.96 | 2685180.96 |  | COA,FPTA,SCCTCCU | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | 10/09/25 | IAR # 20251201-003C | ONGOING
310400100001000 | PROCUREMENT OF NUTRITIOUS FOOD PRODUCTS FOR THE IMPLEMENTATION OF SBFP FOR SY 2025-2026 “LOT E-PROCUREMENT OF COOKIES | SGOD | NO | NP-53.1-TFB | 04/21/25 | 11/13/25 | 11/21/25 | 11/25/25 | 11/25/25 | 11/26/25 11/27/25 | 11/26/25 11/27/25 | 2025-12-02 | 2025-12-10 | 2025-12-16 | 2025-12-17 | ONGOING | ONGOING | RO1-25-0083 | 3144240 | 3144240 |  | 2766931.2 | 2766931.2 |  | COA,FPTA,SCCTCCU | 11/14/25 | 11/14/25 | 11/14/25 | 11/14/25 | 11/14/25 | IAR #20260107-001A | ONGOING
310500100001000 | PROCUREMENT OF MEALS AND SNACKS FOR THE CONDUCT OF DIVISION CONFERENCE ON THE DEVELOPMENT OF HRD STRATEGIC INTERVENTION PROGRAMS | SGOD | NO | Competitive Bidding | 08/27/25 | 08/19/25 | 08/27/25 | 2025-09-09 | 2025-09-09 | 09/10/25 09/11/25 | 09/10/25 09/11/25 | 2025-09-11 | 2025-09-20 | 2025-10-07 | 2025-10-09 | ONGOING | ONGOING | HRD GAA 2024 | 84000 | 84000 |  | 83720 | 83720 |  | COA,FPTA,SCCTCCU | 08/11/25 | 08/11/25 | 08/11/25 | 08/11/25 | 08/11/25 | ONGOING | ONGOING
310200100004000 | PRINTING AND DELIVERY OF STORY BOOKS | CID | NO | NP-53.9 - Small Value Procurement | N/A | 2025-12-12 | N/A | 12/19/25 | 12/19/25 | N/A | N/A | 12/19/25 | 12/26/25 | 2025-12-26 | 12/26/25 | 01/12/2026 | ONGOING | RO1-24-1750 | 277355 | 277355 |  | 260658.23 | 260658.23 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
5020301002 | COA OFFICE SUPPLIES FOR CY 2025 | OSDS | NO | Shopping | N/A | 12/16/25 | N/A | 12/19/25 | 12/19/25 | N/A | N/A | 12/19/25 | N/A | 2025-12-26 | N/A | ONGOING | ONGOING | GAS MOOE 2025 | 49500 | 49500 |  | 45648 | 45648 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
310300100003000 | PRINTING AND DELIVERY OF LEARNING PACKETS | CID | NO | NP-53.9 - Small Value Procurement | N/A | 11/26/25 | N/A | 12/03/25 | 12/03/25 | N/A | N/A | 12/04/25 | 12/19/25 | 12/26/25 | 12/26/25 | 01/12/2026 | ONGOING | RO1-24-1076 | 626366.4 | 626366.4 |  | 438456.48 | 438456.48 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100006000 | ESTABLISHMENT OF LEARNER SUPPORT CENTER AND PROCUREMENT OF SUPPLIES AND EQUIPMENT ESSENTIAL FOR THE OPERATIONS OF THE HEALTH AND WELLNESS HUB (REBID) | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 12/16/25 | NA | 12/19/25 | 12/19/25 | N/A | NA | 12/19/25 | 12/23/25 | 2025-12-23 | 12/26/25 | ONGOING | ONGOING | ROI-24-1953 | 100000 | 100000 |  | 91940 | 91940 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100001000 | PROCUREMENT OF SPORTS SUPPLIES AND EQUIPMENT | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/17/25 | N/A | 12/19/25 | 12/19/25 | N/A | NA | 12/19/25 | 12/19/2025 | 2025-12-23 | 2025-12-23 | ONGOING | ONGOING | OSEC-1-25-02158 | 140247.5 | 140247.5 |  | 138830 | 138830 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
310100100003000 | PROCUREMENT OF ARAL PROGRAM ADVOCACY SHIRTS | CID | NO | NP-53.9 - Small Value Procurement | N/A | 12/11/25 | N/A | 12/19/25 | 12/19/25 | N/A | N/A | 12/19/25 | N/A | 2025-12-23 | N/A | ONGOING | ONGOING | RO1-25-1799 | 26000 | 26000 |  | 26600 | 26600 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100009000 | PROCUREMENT OF SUPPLIES AND MATERIALS FOR LRP ON WHEELS PERFORMANCE | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 12/11/25 | N/A | 12/19/25 | 12/19/25 | N/A | N/A | 12/19/25 | N/A | 2025-12-23 | N/A | ONGOING | ONGOING | RO1-25-1002 | 10000 | 10000 |  | 9971.75 | 9971.75 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100010000 | PROCUREMENT OF SUPPLIES AND OTHER MATERIALS | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 11/25/25 | N/A | 2025-03-12 | 2025-03-12 | N/A | N/A | 2025-03-12 | 2025-03-12 | 2025-12-26 | 2025-12-26 | ONGOING | ONGOING | ROI-24-1722 | 58000 | 58000 |  | 53380 | 53380 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100011000 | PROCUREMENT OF TRAUMA BAGS WITH CONTENTS | SGOD | NO | NP-53.9 - Small Value Procurement | N/A | 11/18/25 | N/A | 11/25/25 | 11/25/25 | N/A | N/A | 11/25/25 | 11/25/25 | 2025-12-23 | 2025-12-23 | ONGOING | ONGOING | RO1-25-0780 | 264000 | 264000 |  | 179980 | 179980 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
310100100003000 | PROCUREMENT AND DELIVERY OF KINDERGARTEN LITERACY AND NUMERACY KITS | CID | NO | NP-53.9 - Small Value Procurement | N/A | 11/12/25 | N/A | 11/21/25 | 11/21/25 | N/A | N/A | 11/21/25 | N/A | 2025-12-17 | N/A | ONGOING | ONGOING | RO1-25-2141 | 39690 | 39690 |  | 33000 | 33000 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
200000100010000 | PROCUREMENT OF MEALS AND SNACKS WITH ACCOMMODATION AND FUNCTION HALL FOR LEARNER RIGHTS AND PROTECTION COMMITTEE FUNCTIONALITY TRAINING FOR SECONDARY SCHOOLS OF SDO SAN CARLOS CITY (REBID) | SGOD | NO | NP-53.9 - Small Value Procurement | NA | 12/12/25 | NA | 12/22/25 | 12/22/25 | N/A | NA | 12/22/25 |  | 2025-12-26 |  | ONGOING | ONGOING | RO1-25-2060 | 420000 | 420000 |  | 420000 | 420000 |  | NA | NA | NA | NA | NA | NA | ONGOING | ONGOING
Total Alloted Budget of On-going Procurement Activities | [18 empty] | 10182438.9
Total Contract Price of On-going Procurement Actitvites Conducted | [18 empty] | 9175302.02
Total Savings of On-going (Total Alloted Budget - Total Contract Price) | [18 empty] | 1007136.88
| Prepared by: | [6 empty] | Recommended for Approval by: | [5 empty] | APPROVED:
| ATTY. MARDE E. PALMA | [5 empty] | DOMINGO L. LAUD, EdD, CESO VI | [7 empty] | DIOSDADO I. CAYABYAB, CESO VI
| Attorney III | [5 empty] | Assistant Schools Division Superintendent | [7 empty] | Schools Division Superintendent
| BAC Secretariat Chairperson | [5 empty] | BAC Chairperson | [7 empty] | Head of the Procuring Entity
Formulas:
Eligibility Check = [Sub/Open of Bids]